## Strat Goal 1- Youth Service
FOCUS AREA 1 Delivering Youth Services Goal: We provide consistent and responsive services to young people Outcomes: ➢ Young people are connected and contribute to the community and each other. ➢ Young people are linked to supports they require. ➢ Young people are provided with opportunities to grow and develop. Rationale: We E.Oieve a consistent and evidenced informed approach is essential to the ongoing wellbeing of young people and the organisation. | Youth Service Operational Plan: EXAMPLE
| Strategic Goal 1 | Delivering Youth Services Goal: We provide consistent and responsive services to young people
| Project/Program Details | Activities | Target or Deadline | Progress Report | Outcomes ¦ Outputs
| Program Name: Fortnightly Friday night (relationship building) .......................................................... Outcome linked to Strategic plan: ➢ Young people are connected and contribute to the community and each other. .......................................................... Objectives: Bulding relationships with staff and each other. An oportuninty to pariciapte, socialise and have fun. ........................................................... Partners: Neighbourhood Houses and Council ............................................................ Staff: Coordinator: ####### Support: | Set dates, determine activites and venues. Survey parents and young people. Pick up and drop off on the bus. Potential outreach via bus. Advertise Mountain Monthly and schools. Posters in various locations throughout the region. Request the Neighbourhood Houses and Council to distribute through their networks. | Planning three months ahead minimum. By January 31st have covered Feb - April Advertise MM 14th of each month and schools newsletters. |  | # young people engage each program #parents enquiring as a result of the marketing #anecdotal feedback survey results
|  | Design canteen "menu," source products | Dinner, snacks and hot chocolate on offer at canteen (income generation for Youth Service) 1 volunteer assist with canteen Young people buy food/consume food or hot chocolate. Eventually move to a youth participation model where young people can run the canteen, dinner and the evening with support of staff. |  | $ raised for Youth Services
|  | Young people attend the evening and are surveyed. | 10 young people attend 1st week 15 young people attend 2nd week etc 80% yp provide feedback. |  | Numbers attended AND % of yp who rated the activity as great or excellent etc
|  | Compile survey responses, design any new project briefs and budgets as required and report back to young people and CoM | Satisfaction survey New activities survey Design new activities for young people to participate in
| Program Name: Youth Service Holiday Program Mid Year............................................................... Outcome linked to Strategic plan: ➢ Young people are provided with opportunities to grow and develop. ---------------------------------------------------- Objectives: To deliver fun, interactive and diverse activities to young people Youth workers build relationships with young people Young people particpate in the design of future programs ............................................................ Partners: Schools Multitude of activity providers .......................................................... Staff: Lead: ####### Support: ####### and casual pool staff | Design program each holidays (set date, activities etc) Marketing - design brochure/posters, newsletters (schools and Youth Service DB), MM, Mail out through Post Office, KRNH brochures and sms broadcasts, social media. Events on website for sign up to program/payment Additional Information sheets Staff Roster | 10 young people attend minimum for excursions 20 young people minimum for incursions 2 youth workers attend Feedback collected from every young person Build database of providers Debrief - 10 minute end of day Overall program Debrief/celebrations Program designed and announced one month prior to school holidays begin
| Program Name: Weekly Drop in Wednesdays ............................................................... Outcome linked to Strategic plan: ➢ Young people are connected and contribute to the community and each other. ➢ Young people are linked to supports they require. ➢ Young people are provided with opportunities to grow and develop. ---------------------------------------------------- Objectives: Provide a safe and accessible place where young people can engage with each other, access support from a youth worker, develop social skills and emotional matuirty. ............................................................ Partners: Schools and community services organisations .......................................................... Staff: Lead: ####### (ensure food is ordered, bus pick up, final decision) Support: #####(support to placement students) and casual staff | ART (through the alliance) MUSIC SPORTS AND OUTDOOR REC BOLLYGUM VISIT (if all good) Group work | Meals provide an opportuntiy Dinner provided by 6pm #minimum 20 young people each week |  | Young people are supported to develop social competence Increase emotional matuirty #young people attending and returning Feedback from young people - survey (twice per year)
MEAL PLAN: WK 1: Baked Potatoes with toppings WK 2: Bolagnaise sauce - either lasagne or spaghetti OR Carbonara WK 3: Bread and Chicken Stew /Beef Stew WK 4: Crumbed fish fillets and salad or vegie
| Program Name: Case Management / Personal Support ............................................................... Outcome linked to Strategic plan: ➢ Young people are linked to supports they require. ➢ Young people are provided with opportunities to grow and develop. ---------------------------------------------------- Objectives: To support vulnerable young people who are at risk of disengagement (from school work or community) to set goals and take positive steps forward in overcoming their barriers ............................................................ Partners: Many agencies .......................................................... Staff: Case Manager: ####### Internal Supervisor: ####### | Intake | minimum: One for each client |  | #of young people
|  | Assessments | minimum: One for each client |  | # of young people # and type barrier
|  | Referral (and ensuring refferral is working well) | minimum of one follow up for each referral In all instances ensure that where it's assessed as required referral is provided. |  | # of referrals place/org name
|  | Advocacy | minimum of one follow up for each referral |  | # of meetings/representations to other orgs
|  | Planning with young person | minimum: One for each client |  | Development plan
|  | Goal Setting and strengths recognition | minimum: Five times for each client |  | Development plan/ mind mapping/ tool box
|  | Reflecting & Re-assessing | minimum: Five times for each client |  | Development plan
|  | Partnering with relevant agency/recreation service to encourage participation | To enagage with all organisations involved and seek out where there is no other current involvement |  | # and type of program
|  | Family engagement | To enagage with at least one familiy member for each client |  | #relationships with family increased engagement of family
|  | Debrief & Supervision in-house | Minimum five times per year |  | # provided
|  | Clinical Supervision | Minimum five times per year |  | #provided

## Strat Goal 2- Youth Voice
FOCUS AREA 2 The Youth Voice. Goal: To provide an environment where young people are valued, respected, and encouraged to participate in decision making Outcome: ➢ Young people have a voice in their community ➢ Youth Service demonstrates and supports young people's voices and opinions being heard ➢ Young people own the youth space. ➢ Young people are valued for their input and contribution Rationale: We E.Oieve that all young people should be involved in the decisions that impact their lives. | Youth Service Operational Plan: EXAMPLE
| Strategic Goal 2 | The Youth Voice Goal: To provide an environment where young people are valued, respected, and encouraged to participate in decision making
| Project/Program Details | Activities | Target or Deadline | Progress Report | Outcomes ¦ Outputs
| Program Name: Young Leaders Group: .......................................................... Outcome linked to Strategic plan: ➢ Young people have a voice in their community ➢ Youth Service demonstrates and supports young people's voices and opinions being heard ➢ Young people are valued for their input and contribution .......................................................... Partners: ######### ######### ........................................................... Objectives: Raising the profile of young people in the Ranges. Providing young people with the tools they need to make a difference in their community in ways they identify. ............................................................ Staff: Lead: ####### Youth facilitator: Kate Chalmers | Team Building | Early in the Year: Team building intensive delivered |  | #of young people involved Forming a team Taking action as a team (planning a small project) Completing challenges delivering a small project
|  | Leadership Skill Development | Ongoing throughout the year Fortnightly meetings for the Steer (depending on the Steer) |  | Skills/strengths identification sheet Possible evaluation pre and post program to measure improvement in skills
|  | Goal Setting (individual and group) | Ongoing throughout the year Plan implement and evlauate a project of the Teams choice (responding to a community need) |  | #goals set Plan (project brief) Implementation Plan Roles defined Measures in place Debrief Feedback or participation of other in the project delivered by the group.
|  | Recruitment | End of Year starts Mid November - January Maximum: 10 young people Minimum: 1 Youth faciliator |  | # of young people recruited # activities undertaken to achieve recruitment # applicants or those Expressions of interest
| Program Name: The Youth Voice - articles and local Media coverage .......................................................... Outcome linked to Strategic plan: ➢ Young people have a voice in their community ➢ Youth Service demonstrates and supports young people's voices and opinions being heard ➢ Young people are valued for their input and contribution .......................................................... Partners: Local media outlets ........................................................... Objectives: To offer a platform where young people can express their opinions. ............................................................ Staff: Lead: ####### | Engage young people to write an article guaranteed to be pulished in local media, on our Facebook Page and on our Website. | Monthly article from 1 young person Required by 15th of each month Social Share Web upload |  | # of young people engaged # of people reached on social Feeback from community

## Strat Goal 3 -Partnerships
FOCUS AREA 3 Partnerships/Stakeholder Engagement Goal: Creating sustainable partnerships Outcomes: ➢ Increased capacity to deliver relevant youth services. ➢ We have created sustainable relationships. ➢ We generate revenue, by offering the facilities to approved applicants, to support youth programs. ➢ Provided opportunities and support for people to volunteer and contribute to the development of Youth Service. Rationale: We E.Oieve in working with relevant stakeholders to deliver consistent, viable and meaningful youth services. | Youth Service Operational Plan: EXAMPLE
| Strategic Goal 3 | Partnerships/Stakeholder Engagement Goal: Creating sustainable partnerships
| Project/Program Details | Activities | Target or Deadline | Progress Report | Outcomes ¦ Outputs
| Program Name: Youth Service Service Links .............................................................. Outcome linked to Strategic plan: ➢ Increased capacity to deliver relevant youth services. ---------------------------------------------------- Objectives: Work with specialist providers to establish a diverse range of specialist youth services to provide to young people ............................................................ Partners: Mental Health Agencies Drug and Alcohol Services Anger Management Programs Tutors - qualified Primary Health Professionals Domestic Violence Professionals Short Term Education Providers .......................................................... Staff: Lead: ####### Support: ####### | Contact multiple agencies and understand the extent of their service areas, responsibilities, opportunities to deliver, contraints etc. | Ongoing development
|  | Develop a refferal pathway with services and schools Shared Vision Defined Roles | Ongoing development though
Promote the availability of the service widely and ensure they have a safe and welcoming environment to engage with young people.
| Program Name: Building partnerships ............................................................... Outcome linked to Strategic plan: Outcomes: ➢ Increased capacity to deliver relevant youth services. ➢ We have created sustainable relationships. ➢ We generate revenue, by offering the facilities to approved applicants, to support youth programs. ➢ Provided opportunities and support for people to volunteer and contribute to the development of Youth Service. ---------------------------------------------------- Objectives: To build Partnership work into all projects and programs in Youth Service ............................................................ Staff: All staff and Committee of Management | Add Partners to all facets of stratgeic plan where feasible and possible. | ongoing |  | MoUs applied where required. Numer of partner organisations attending AGM
|  | Recognise and celebrate the effort of partners |  |  | Annual celebration

## Strat Goal 4- Org Capability
FOCUS AREA 4 Organisational Capability Goal: We are a thriving organisation recognised for delivering quality youth services underpinned by good governance. Outcomes: ➢ We evaluate our services and are accountable to all stakeholders. ➢ We have an active strategy for financial resourcing and income diversification into the future, reviewed regularly. ➢ We have a strong sense of identity that is recognised by key stakeholders and reinforced by a marketing strategy. ➢ Staff satisfaction is high. Staff are appropriately qualified and well supported by the Organisation. ➢ The Committee of Management is committed to improvement and is well trained in Governance best practice (including compliance). Rationale: We E.Oieve in building on strengths to develop Youth Service to it's full potential. | Youth Service Operational Plan: EXAMPLE
Strategic Goal 4: Organisational Capability Goal: We are a thriving organisation recognised for delivering quality youth services underpinned by good governance.
Key Goal: Ensure compliance with funding contracts, financial responsibilities, CoM responsibilities, HR responsibilities, Office management, ATO/CAV/ACNC legislation, Research and Policy Development, Funding Submissions, Staff Training
| Objective | Activity | DEADLINES | Outcomes ¦ Outputs | PROGRESS | Responsible
| Compliance with Funding contracts | Review the contracts and record milestone sand deadlines in diary - FRRR (multiple projects) - Kinglake Ranges Foundation - Catholic Care | Ongoing | # Milestones achieved |  | Executive Office ¦ Manager ¦ Coordinator
| Reporting is completed in time-lines required | Consult with partners, staff and CoM | Ongoing | All requirements of reports are completed and delivered by due date |  | Executive Office ¦ Manager ¦ Coordinator
| Review Milestone ensure on track | Reflect on Operational Plan or Project Plan and record achievements - | Quarterly or as required. | # Milestones are met on time or new milestones set or adjusted as required |  | Executive Office ¦ Manager ¦ Coordinator
| Financial Statements prepared each month | Using our software track financial progress | Ongoing | Financial records match projected budget |  | Executive Office ¦ Manager ¦ Coordinator
| Insurance | Review all Insurances. Quotes from not-for-profit insurance providers to ensure best deals available each year | 2019-12-01 | Compliance requirments met Always insured appropriately Risk management and Risk mitigation applied to all activities |  | Executive Office ¦ Manager ¦ Coordinator
| Youth Service maintains property insurance as required | NFP Package | 2019-12-02 | insured |  | Executive Office ¦ Manager ¦ Coordinator
| Youth Service maintains directors and officers legal liability indemnity insurance cover | NFP Package | 2019-12-03 | insured |  | Executive Office ¦ Manager ¦ Coordinator
| Youth Service maintains insurance in accordance with the requirements of the Accident Compensation Act 1985 and the Accident Compensation (WorkCover Insurance) Act 1993 | WorkSafe Insurance procurement | 2019-09-01 | Information is updated annualy Work safe posters and policies re-inforced twice per year with staff |  | Executive Office ¦ Manager ¦ Coordinator
| Financial Responsibilities |  |  |  |  | Executive Office ¦ Manager ¦ Coordinator
Timely payment and processing of wages
| CoM responsibilities |  |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| AGM date is set in timely manner with an engaging Guest Speaker to motivate community attendance and new memberships | Prepare annual report including: Presidents Report EO Report Treasurers Report/ Audit Report Good news stories |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| CoM Membership Register and Membership Drive Better community presence should lead to increased membership | Record of all members of Youth Service Work toward membership drive Better community presence should lead to increased membership |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| CoM is aware of policy matters, financial status, significant operational matters | CoM is aware of reports, policy matters, discussion papers, forthcoming conferences. |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| CoM members meet at least five (5) times per year including an AGM. | Set all Com dates and circulate meeting request |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| HR Responsibilities |  |  |  |  | Executive Office ¦ Manager ¦ Coordinator
| Staff are provided with a healthy, fun and lively environment where they are encouraged to succeed and enjoy their roles | Create and maintain a culture | Ongoing | Staff and volunteers thrive in their roles. They are supported and guided and are also given the space and opportunity to be themselves and bring their skills to the role. We do not micro-manage our people. |  | Executive Office ¦ Manager ¦ Coordinator
| Staffing is determined on a needs basis, reflecting projects being implemented | Regular catch ups | Minimum monthly | Staff are not overworked and have channels to discuss time managment and any issue relating to role: leads to better retention |  | Executive Office ¦ Manager ¦ Coordinator
| Staff contracts are signed at beginning of year, or as necessary. | Ongoing oversight - record dates in diary | Ongoing | Best practice contract management |  | Executive Office ¦ Manager ¦ Coordinator
| Office Management |  |  |  |  | E.O
| IT systems | Analysis of hardware and software systems and policies | Annual or once every two years | We have the nest available technology that saves time and money for the organisation |  | E.O
| Website devleopment | Maintain relationship with IT to ensure server environment and cpanel access estimated cost $350 and maintenance |  | We have a well supported IT enviroment |  | E.O
| Website ongoing uodates | All staff to ensure their web pages are up to date, sending new information to E.O to upload. | Quarterly reviews | Organisation has a useful and up to date website: community can renly on information |  | E.O: ALL staff
| Phone systems | Analysis of phones, plans, gigabytes available etc through Telstra | Annually as plans are expiring | Organisation recieves best deals available to save money |  | E.O
ATO / CAV/ACNC Legislation
| Timely preparation, lodgement and payment of all IAS and BAS. | INsert due dates to shared calendar with book keeper | Quartelry or as required | lodgement and payment of all IAS and BAS as due |  | Book keeper/ E.O/Secretary/Treasurer
| Annual Statement lodged with CAV as required. | Secretary lodge online statement | November annualy | Compliance met |  | E.O/ Secretary
| Annual Statement lodged with ACNC as required. | Pending acceptance of application to ACNC | Dependent on ACNC | Youth Service is a transparent not-for profit meeting best practice standards through the Commission |  | E.O/Secretary/Treasurer
| Research and Policy and Process Development |  |  |  |  | E.O
| Enure policy documents and staff handbooks are reviewed and updated to reflect the Youth Sector | Ensure new Child Safe Standards are in accordance with legislation following the Royal Commision | Janualy 1st 2019 |  |  | E.O
| Process for delivering Youth Service activities | Permission Forms Handling allergies Gathering Feedback |  |  |  | E.O
| Funding Submissions ¦ Fundraising Activities |  |  |  |  | E.O
| Review all data and information and feedback from young people and apply for funding to meet community need | Compile a Grants wish list - define the Youth Service story and ensure all our data is up to date Seek out funding that provides recurrent funding | 2019-01-01 |  |  | E.O
| BUILDING MAINTANENCE |  |  |  |  | E.O
| Building is safe and accessable | Risk Management - OHS audit Emergency Lighting UV Filtration system upkeep Cleaners engaged Alarms and Doors tested Maintainence Book reviewed and updated Handover notes prepared Lease paid User group rules followed Toilet maintence Gutters Grass Kitchen machinery serviced | Ongoing | Building complies with above average standard required to deliver youth services |  | E.O
| Risk Management | Risk Management in place for all programs All staff and violunteers are aware of procedures Emergency and Evacuation procedures in place Insurance certificates available and checked from all providers of activities for young people |  | Risk mitigated and safety ensured |  | E.O